## Overview
Testing Schedule
Customer Name
| Total Number of Test Scripts |  | Test scripts PASSED |  | Test scripts FAILED
| 126 |  | 0 |  | 0
|  | Failed Nice to Have Tests |  | Failed Go-Live Critical Tests
|  | 0 |  | 0
In order to help users with testing in Financials, the core users who attended the Training Courses will have the PDF copies of the course manuals to refer back to. The following links can be also be used as useful learning material throughout testing:
MyWorkplace HelpDocs: |  |  |  | Click Here
Financials HelpDocs: |  |  |  | Click Here
Procurement Portals HelpDocs: |  |  |  | Click Here

## Go Live Criteria
Go Live Criteria
The following criteria needs to be met, prior to the Go Live date. This checklist will be referred to during the Go Live Readiness meeting towards the end of your Financials implementation.
1 | Testing has been completed for core staff/wider team
2 | Integration tests are completed (3 ITKs)
3 | Go Live critical failures are reported on the Problems & Queries Tracker
4 | All Go Live critical failures retested and resolved
5 | Business critical reports are available and tested
6 | Relevant documentation is requested and issued out to core staff/wider team

## System Admin & Security
| Module : | System Admin of My Workplace & User Security
| Business Process: | Standard | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | The functionality within My Workplace is working and has been fully tested based on company specific processes.
| Test Data / Pre-requisites: |  | Data Migration has been completed. 6 designated users have completed the System Admin of My Workplace & User Security Overview eLearning and Course.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback |  | Nice to Have | Y
MyWorkplace - Users must have the correct Groups enabled against their record in order to perform these tests:
1A | Create a Desk | MyWorkplace | Create a Desk | A new Desk is available for the user in My Workplace | [7 empty] | 1 | Go Live Critical
1B | Create an Applet | MyWorkplace | Create an Applet | A new applet can be seen on the users desk within My Workplace | [7 empty] | 1 | Showstopper
1C |  | MyWorkplace | Upload a file into Files Management | A file is successfully uploaded and can be found in Files Management | [7 empty] | 1
1D |  | MyWorkplace | Download a file from Files Management | A file is successfully downloaded from Files Management | [7 empty] | 1 | Go Live Critical
1E |  | MyWorkplace | Create a My Workplace User | A new user appears in the user list within My Workplace | [7 empty] | 1 | Showstopper
Financials - Users must be assigned to the STD security group to perform these tests
2A |  | Systems Admin - System Wide Controls - Users & Roles - Combined User Setup | Create a Combined User | A new user appears in the Combined User listing | [7 empty] | 1
2B |  | Systems Admin - System Wide Controls - Users & Roles - Security - GL Range Codes | Create a GL Range Code | A new GL Range Code exists | [7 empty] | 1 | Go Live Critical
2C |  | Systems Admin - System Wide Controls - Users & Roles - Security - GL Access Codes | Create a GL Access Code | A new GL Access Code exists | [7 empty] | 1 | Showstopper
2D |  | Systems Admin - System Wide Controls - Users & Roles - Security - GL Security Group Access Code | Create a GL Security Group Access Code | A new GL Security Group Access Code exists | [7 empty] | 1
End Test
| Total Steps: |  | 9 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## General Ledger
| Module : | General Ledger
| Business Process: | Standard | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | The functionality for General Ledger users is working and hs been fully tested based on company specific processes.
| Test Data / Pre-requisites: |  | Data Migration has been completed. 6 designated users have completed the General Ledger Overview eLearning and course.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback |  | Nice to Have | Y
Financials - Users must be assigned to the STD security group to perform these tests
1A | Creating a Journal | General Ledger - GL Processes - GL Data Entry - Journal Entry | Create a Standard Journal | Post an adjustment to one period | [7 empty] | 1 | Go Live Critical
1B |  | Upload a Journal using the Journal Excel Uploader | Upload a Journal using the Journal Excel Uploader | Initiate, validate and update to submit journal, view success report from Report worksheet | [7 empty] | 1 | Showstopper
1C |  | Upload a Budget using the Journal Excel Uploader | Upload a Budget using the Journal Excel Uploader | Initiate, validate and update to submit journal, view success report from Report worksheet | [7 empty] | 1
1D | Create a Reversing Journal | General Ledger - GL Processes - GL Data Entry - Journal Entry | Create a Reversing Journal | Reverses the journal into the next period | [7 empty] | 1 | Go Live Critical
1E | Create a Recurring Journal | General Ledger - GL Processes - GL Data Entry - Journal Entry | Create a Recurring Journal | Post an adjustment to multiple period | [7 empty] | 1 | Showstopper
1F | List Journals | General Ledger - GL Processes - GL Data Entry - List Journals | View Journal List | List of Journals with different status are displayed for the current day | [7 empty] | 1
1G |  | General Ledger - GL Processes - GL Transfers - Detail Transfers | Create a Detail Transfer | If you have ICA switched on this cannot be performed. Transfer a transaction from a wrong account to the correct account | [7 empty] | 1 | Go Live Critical
1H |  | General Ledger - GL Processes - GL Transfers - Full Journal Transfers | Create a Full Batch Transfer | If you have ICA switched on this cannot be performed. This will cancel out the original batch in the original period | [7 empty] | 1 | Showstopper
1I |  | General Ledger - GL Processes - GL Transfers - Full Journal Transfers | Create a Full Batch Reversal | If you have ICA switched on this cannot be performed. User is deactivated and does not appear in the listing as an active record | [7 empty] | 1
1J | Perform Period End for GL | General Ledger - GL Processes - Period/Year End Close - GL Period and Year End | Perform Period End for GL | The period for General Ledger only is closed and the next period is opened | [7 empty] | 1
1K | Perform Period End for System Modules | General Ledger - GL Processes - Period/Year End Close - GL Period and Year End | Perform Period End for System Modules | The period for AP, PM, IM and AR only is closed and the next period is opened. General Ledger period is not moved | [7 empty] | 1
1L | Perform Year End | General Ledger - GL Processes - Period/Year End Close - GL Period and Year End | Perform Year End | The adjustment period for the previous year is closed and the current year is closed. The following year is opened and the years adjustment period is opened | [7 empty] | 1
General Ledger Enquiries
2A |  | General Ledger - GL Enquiries - Transactions by Account Code | Run a Transactions by Account Code Enquiry | [8 empty] | 1
2B |  | General Ledger - GL Enquiries - Balance Sheet | Run a Balance Sheet Enquiry | [8 empty] | 1
2C |  | General Ledger - GL Enquiries - Profit and Loss | Run a Profit and Loss Enquiry | [8 empty] | 1
2D |  | General Ledger - GL Enquiries - Structure Net Balance Enquiry | Run a Structured Net Balance Enquiry | [8 empty] | 1
End Test
| Total Steps: |  | 16 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## Purchase to Pay
| Module : | Purchase to Pay
| Business Process: | Standard | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | The functionality within Purchase to Pay is working and hs been fully tested based on company specific processes.
| Test Data / Pre-requisites: |  | Data Migration has been completed. 6 designated users have completed the Purchase to Pay Overview eLearning and course.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback
Financials - Users must be assigned to the STD security group to perform these tests
1A | Create a Supplier | Accounts Payable - AP Processes - Suppliers - Maintain Suppliers | Create a Supplier | A new Supplier exists in the Supplier list | [7 empty] | 1 | Go Live Critical | Y
1B | Create a Supplier | Accounts Payable - AP Processes - Suppliers - Maintain Suppliers | Bank Validator | If Bank Validator has been purchased and enabled, when setting the Sort Code and Account Number, selecting Validate should complete successfully | [7 empty] | 1 | Go Live Critical | Y
My Workplace - Procurement Portal
2A | Create an Order | Orders | Create a Purchase Order | A new Purchase Order can be found from the Procurement Portal | [7 empty] | 1
2B | Copy an Order | Enquries - Orders | Copy a Purchase Order | A new Purchase Order can be found from the Procurement Portal | [7 empty] | 1
2C | Revise an Order | Enquries - Orders | Revise a Purchase Order | [8 empty] | 1
2D | Cancel an Order | Enquries - Orders | Cancel a Purchase Order | [8 empty] | 1
2E | Authorise a Purchase Order | Authorisations | Authorise a Purchase Order | [8 empty] | 1
2F | Authorise a Purchase Order on behalf | Authorisations - Heirarchy | Authorising a Purchase Order on behalf of another user | [8 empty] | 1
2G | Create a Goods Receipt | Receipts | Process a Goods Received Note | [8 empty] | 1
2H | Cancel a Goods Receipt | Enquiries - Receipts | Cancel a Goods Received Note | [8 empty] | 1
Financials - Users must be assigned to the STD security group to perform these tests
3A | Create a Logged Invoice | Accounts Payable - AP Processes - AP Data Entry - Log Invoices | Create a Logged Invoice | [8 empty] | 1
3B | Create an Entered Invoice (No Purchase Order) | Accounts Payable - AP Processes - AP Data Entry - Enter Invoices | Create an Entered Invoice (No Purchase Order) | [8 empty] | 1
3C |  | Accounts Payable - AP Processes - AP Data Entry - Enter Invoices | Create an Entered Invoice (Purchase Order) | [8 empty] | 1
3D |  | Accounts Payable - AP Processes - AP Data Entry - Enter Credit Notes | Create an Entered Credit Note | [8 empty] | 1
3E |  | Accounts Payable - AP Processes - Transaction Maintenance - Amendment | Amend an Entered Invoice | [8 empty] | 1
3F |  | Accounts Payable - AP Processes - Transaction Maintenance - Suspend/Release | Suspend an Entered Invoice | [8 empty] | 1
3G |  | Accounts Payable - AP Processes - Transaction Maintenance - Suspend/Release | Release an Suspended Invoice | [8 empty] | 1
3H |  | Accounts Payable - AP Processes - Transaction Maintenance - Cancellation | Cancel an Entered Invoice | [8 empty] | 1
3I | Payment Processing | Accounts Payable - AP Processes - Payment Processing - Create Payment Schedules | Processing a Payment Schedule | [8 empty] | 1
Purchase to Pay Enquiries
4A | [11 empty] | 1
4B | [11 empty] | 1
4C | [11 empty] | 1
1
1
1
| End Test | [11 empty] | Showstopper
| Total Steps: |  | 21 |  |  |  | 0 | 0 |  |  |  |  | Nice to Have
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## Accounts Receivable
| Module : | Accounts Receivable & Sales Invoicing
| Business Process: | Standard | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | The functionality within Accounts Receivable is working and hs been fully tested based on company specific processes.
| Test Data / Pre-requisites: |  | Data Migration has been completed. 6 designated users have completed the Accounts Receivable & Sales Invoicing Overview eLearning and course.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback
Financials - Users must be assigned to the STD security group to perform these tests
1A | Creat a Customer account | Accounts Receivable - AR Processes - Customers - Maintain Customers | Create a Customer | [8 empty] | 1 | Go Live Critical | Y
1B | Create an Invoice | Accounts Receivable - AR Processes - AR Data Entry - Insert Invoice/Credit Note | Create an Invoice | [8 empty] | 1 | Showstopper
1C | Create a Credit Note | Accounts Receivable - AR Processes - AR Data Entry - Insert Invoice/Credit Note | Create a Credit Note | [8 empty] | 1 | Nice to Have
1D |  | Accounts Receivable - AR Processes - AR Data Entry - Cash/Adjustment Entry | Create a Cash Receipt | [8 empty] | 1
1E |  | Accounts Receivable - AR Processes - AR Data Entry - Cash/Adjustment Entry | Enter a Cash Transaction | [8 empty] | 1
1F |  | Accounts Receivable - AR Processes - AR Data Entry - Cash/Adjustment Entry | Record an Adjustment on a Customer Account | [8 empty] | 1
1G |  |  | Perform an Overpayment | [8 empty] | 1
1H |  |  | Perform an Refund | [8 empty] | 1
Accounts Receivable Enquiries
2A | Run a Customer Account Enquiry | Accounts Receivable - AR Enquiries - Transaction Enquiries - Customer Account Enquiry | Run a Customer Account Enquiry | [8 empty] | 1
2B | Run a Transaction Enquiry | Accounts Receivable - AR Enquiries - Transaction Enquiries - Transactions by Customer | Run a Transaction Enquiry | [8 empty] | 1
2C |  |  | Run a Payment Details Enquiry | [8 empty] | 1
2D |  |  | Run a GL Linked Enquiry | [8 empty] | 1
2E |  |  | Run an Allocation Enquiry | [8 empty] | 1
End Test
| Total Steps: |  | 13 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## Fixed Assets
| Module : | Fixed Assets
| Business Process: | Standard | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | The functionality within Fixed Assets is working and hs been fully tested based on company specific processes.
| Test Data / Pre-requisites: |  | Data Migration has been completed. 6 designated users have completed the Fixed Assets Overview eLearning and course.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback
Financials - Users must be assigned to the STD security group to perform these tests
1A |  |  | Generate Prompt File Entries | [8 empty] | 1 | Nice to Have | Y
1B | Create an Asset from the Prompt File | Fixed Assets - FA Processes - Asset Maintenance - Prompt File | Create an Asset from the Prompt File | [8 empty] | 1 | Go Live Critical
1C | Join Items on the Prompt File | Fixed Assets - FA Processes - Asset Maintenance - Prompt File | Join items on the Prompt File | [8 empty] | 1
1D |  | Fixed Assets - FA Processes - Asset Maintenance - Prompt File | Split items on the Prompt File | [8 empty] | 1
1E |  | Fixed Assets - FA Processes - Asset Maintenance - Maintain Asset Register | Adding value to an asset | [8 empty] | 1
1F |  | Fixed Assets - FA Processes - Asset Maintenance - Maintain Asset Register | Directly insert an asset | [8 empty] | 1
1G |  | Fixed Assets - FA Processes - Asset Maintenance - Maintain Asset Register | Create an Initial Correction against an Asset | [8 empty] | 1
1H | Perform an Asset Relife | Fixed Assets - FA Processes - Asset Maintenance - Maintain Asset Register | Perform an Asset Re-Life | [8 empty] | 1
1I | Perform Asset Revaluation | Fixed Assets - FA Processes - Asset Maintenance - Maintain Asset Register | Perform Asset Revaluation | [8 empty] | 1
1J |  | Fixed Assets - FA Processes - Asset Maintenance - Disposals | Create an Asset Transfer | [8 empty] | 1
1K | Create an Asset Disposal | Fixed Assets - FA Processes - Asset Maintenance - Transfers | Create an Asset Disposal | [8 empty] | 1
1L | Perform Period End and Depreciation | Fixed Assets - FA Processes - Asset Maintenance - Submit FA Period End | Perform Period End and ensure Depreciation runs | [8 empty] | 1
1M |  | Fixed Assets - FA Processes - Asset Maintenance - Submit FA Year Close | Perform Year End and ensure Depreciation runs | [8 empty] | 1
Fixed Assets Enquiries
2A |  |  | Run an Asset Register Enquiry | [8 empty] | 1
2B |  | Fixed Assets - FA Enquiries - Company Summary | Run a Company Summary Enquiry | [8 empty] | 1
2C |  | Fixed Assets - FA Enquiries - Offline Forecasting Report | Run a Forecasting Enquiry | [8 empty] | 1
2D |  | Fixed Assets - FA Enquiries - Valuations | Run a Valuation Enquiry | [8 empty] | 1 | Showstopper
2E |  | Fixed Assets - FA Enquiries - Disposals | Run a Disposals Enquiry | [8 empty] | 1
2F |  | Fixed Assets - FA Enquiries - Transfers | Run a Transfer Enquiry | [8 empty] | 1
End Test
| Total Steps: |  | 19 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## Bank Reconciliation
| Module : | Bank Reconciliation
| Business Process: | Standard | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | The functionality within Bank Reconciliation is working and hs been fully tested based on company specific processes.
| Test Data / Pre-requisites: |  | Data Migration has been completed. 6 designated users have completed the Bank Reconciliation Overview eLearning and course.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback
Financials - Users must be assigned to the STD security group to perform these tests
1A |  | Systems Admin - Module Controls - Bank Reconciliation Controls - Bank Codes | Create a Bank Code | A new Bank Code exists in the Bank Code list | [7 empty] | 1 | Nice to Have | Y
1B |  | Systems Admin - Module Controls - Bank Reconciliation Controls - Bank Transaction Types | Create a Bank Transaction Type | A new Transaction Type exists for the Bank in use | [7 empty] | 1 | Go Live Critical
1C |  | Systems Admin - Module Controls - Bank Reconciliation Controls - Bank Transaction Types | Create a Bank Transaction Sub Type | A new Transaction SubType exists for the Transaction Type | [7 empty] | 1
1D |  |  | Prepare the Bank Statement Upload Template | The template matches the template sample that was covered during the training course | [7 empty] | 1
1E |  | Bank Reconciliation - Bank Reconciliation Processes - Bank Reconciliation Statement Takeon | Upload a Bank Statement | The statement successfully loads into Financials with no errors | [7 empty] | 1
1F |  | Bank Reconciliation - Bank Reconciliation Processes - Automatic Reconciliaiton by Code | Process Automatic Reconciliation by Code | The Reconciliation Reports run and show the user that automatic postings have been made or not | [7 empty] | 1
1G |  | Bank Reconciliation - Bank Reconciliation Processes - Automatic Reconciliaiton by Date | Process Automatic Reconciliation by Date | The Reconciliation Reports run and show the user that automatic postings have been made or not | [7 empty] | 1
1H |  | Bank Reconciliation - Bank Reconciliation Processes - Manual Reconciliation | Perform Manual Reconciliation | Transactions are reconciled and are removed from the Reconciliation screen | [7 empty] | 1
1I |  | Bank Reconciliation - Bank Reconciliation Processes - Manual Reconciliation | Create a Journal from Manual Reconciliation | [8 empty] | 1
1J |  | Bank Reconciliation - Bank Reconciliation Processes - Matched Transactions | Unmatch Reconciled Transactions | [8 empty] | 1
Fixed Assets Enquiries
2A |  | Bank Reconciliation - Bank Reconciliation Enquiries - Reconciliation Summary | Run a Company Summary Enquiry | [8 empty] | 1
End Test
| Total Steps: |  | 11 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## Reporting
| Module : | Reporting
| Business Process: | Standard | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | The functionality within Reporting is working and has been fully tested.
| Test Data / Pre-requisites: |  | Data Migration has been completed. 6 designated users have completed the Reporting Overview eLearning and course.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback
MyWorkplace - Users must have the correct Groups enabled against their record in order to perform these tests: Reporting
1A |  |  | Logging In and Familiarising yourself with Reporting | [8 empty] | 1 | Nice to Have | Y
1B |  |  | Creating a sub folder within the Repository | [8 empty] | 1 | Go Live Critical
1C |  |  | Adding a file into the Repository | [8 empty] | 1
1D |  |  | Run a Report | [8 empty] | 1
1E |  |  | Opening an Adhoc View | [8 empty] | 1
1F |  |  | Creating a new Adhoc View | [8 empty] | 1
1G |  |  | Creating a Report from an Adhoc View | [8 empty] | 1
1H |  |  | Create a new Adhoc View and Report | [8 empty] | 1
1I |  |  | Create a Scheduled Job | [8 empty] | 1
1J |  |  | Create Calculated Fields and Measures | [8 empty] | 1
1K |  |  | Create further Adhoc Views | [8 empty] | 1
1L |  |  | Familiarise yourself with Cross Tabs | [8 empty] | 1
1M |  |  | Create NULL Values | [8 empty] | 1
1N |  |  | Create a dynamic balance | [8 empty] | 1
1O |  |  | View data in a Column Chart | [8 empty] | 1
1P |  |  | Create a KPI Chart | [8 empty] | 1
1Q |  |  | Create a new Dashboard | [8 empty] | 1
1R |  |  | Map Filter Parameters | [8 empty] | 1
1S |  |  | Add additional content to your Dashboard | [8 empty] | 1
MyWorkplace
2A |  |  | Create a Private Desk | [8 empty] | 1
2B |  |  | Add an Applet for Reporting/Dashboards | [8 empty] | 1
End Test
| Total Steps: |  | 21 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## BTP
| Module : | Business Tax Portal (BTP)
| Business Process: | Standard | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | The functionality within Business Tax Portal is working and has been fully tested.
| Test Data / Pre-requisites: |  | Reporting Overview eLearning has been completed and Data Migration has been completed
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback
Financials
1A |  |  | Run AP and AR VAT Analysis processes in Update mode for the reporting date | Reports showing the extracted AP and AR transaction and the data matched to GL | [7 empty] | 1 | Nice to Have | Y
1B |  |  | Run RH1 process in summary in reporting date range | Reports showing the extracted AP transaction and the data matched to GL | [7 empty] | 1 | Go Live Critical
1C |  |  | View document report by Company/ICA Element | Shows 9 box breakdown of how VAT is calculated | [7 empty] | 1
1D |  |  | Run RH1 process in Update Mode in reporting date range | Full detail CSV file is produced for submission in BTP | [7 empty] | 1
BTP
2A |  |  | View available files produced | Base edition and Full edition | [7 empty] | 1
2B |  |  | Import File in BTP Import window | Allows you to upload file | [7 empty] | 1
2C |  |  | Delete a report | incorrect file deleted
2D |  |  | Run Import | Report submitted
2E |  |  | View Tax Return Summary | This should match the summary report from e5
End Test
| Total Steps: |  | 6 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## Headstart Forms
| Module : | Headstart Forms AKA Business Process Management (BPM)
| Business Process: | This module is a bolt on so the following testing scenarios should only be followed if BPM has been purchased | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | The forms within BPM are working and have been fully tested based on company specific processes.
| Test Data / Pre-requisites: |  | Tweaks to the forms have been made with a member of the team from OneAdvanced and have been signed off, ready to use for testing.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback
MyWorkplace - BPM
1A |  |  | Create Customer | All mandatory fields completed and customer created | [7 empty] | 1 | Nice to Have | Y
1B |  |  | Create Supplier | All mandatory fields completed and supplier created
1C |  |  | Create Management Code | All mandatory fields completed and Management code created | [7 empty] | 1 | Go Live Critical
1D |  |  | Create Nominal Code | All mandatory fields completed and Nominal Code created | [7 empty] | 1
1E |  |  | Create Sales Invoice | All mandatory fields completed and Sales Invoice created | [7 empty] | 1
1F |  |  | Create a Payment Request
End Test
| Total Steps: |  | 6 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## Document Processing (PIA)
| Module : | Purchasing Invoice Automation (PIA)
| Business Process: | This module is a bolt on so the following testing scenarios should only be followed if PIA has been purchased | Executed By: | User Name
| Author: | OneAdvanced | Execution Date: |  | System: | Company Number Here
| Test Objective / Purpose: |  | Smart Capture and Smart Workflow have been fully tested along with the end to end process with Financials.
| Test Data / Pre-requisites: |  | Data Migration has been completed. 6 designated users have completed the Purchase Invoice Automation Overview eLearning and course.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback
Smart Capture
1A | [11 empty] | 1 | Nice to Have | Y
1B
1C | [11 empty] | 1 | Go Live Critical
1D | [11 empty] | 1
1E | [11 empty] | 1
1F
Smart Workflow
1A | [11 empty] | 1 | Nice to Have | Y
1B
1C | [11 empty] | 1 | Go Live Critical
Financials
1A | [11 empty] | 1 | Nice to Have | Y
1B
1C | [11 empty] | 1 | Go Live Critical
End Test
| Total Steps: |  | 6 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## Analytics (hidden)
| Module : | Analytics
| Business Process: |  | Executed By: | User Name
| Author: |  | Execution Date: |  | System: | Test
| Test Objective / Purpose: |  | The functionality for Analytics is working and hs been fully tested based on company specific processes.
| Test Data / Pre-requisites: |  | Supplier data has been uploaded into the solution.
Test ID | Help Doc | Area of Test (Which process area, e.g. Events) | Scenario (Update as you progress) | Expected Result | Actual Result – Observation or Comments |  | Pass | Fail | Enter if Failed | Advanced Response | Customer Feedback
1A |  | Analytics - Running Reports | Ensure that there are 9 dashboards/reports visible in the Analytics module | All 9 dashboards/reports appear and can be selected | [7 empty] | 1 | Y | Nice to Have
1B |  | Analytics - Running Reports | Use the filters on the right hand side to filter on specific data for each report | Report(s) are filtered correctly | [7 empty] | 1
1C |  | Analytics - Running Reports | Click on data in a visual chart/graph to filter the rest of the page | Report(s) are filtered correctly | [7 empty] | 1
1D |  | Analytics - Running Reports | Utilise the filters within the dashboard, usually at the top of the page | Report(s) are filtered correctly |  | have a general analytics one for everything - sack off individual rows | [5 empty] | 1
1E |  | Analytics - Running Reports | Export a table based on current layout | Table layout displayed within Analytics is exported into excel in the same format | [7 empty] | 1
1F |  | Analytics - Running Reports | Test focus mode within Analytics so that one dashboard can be viewed on a larger scale | Other dashboards disappear from view and the dashboard you focus on is larger | [7 empty] | 1
1G |  | Analytics - Running Reports | For graphs, choose the show as table option to view the data in a different format | The data is no longer in graph format | [7 empty] | 1
1H |  | Analytics - Running Reports | For any dashboard choose the spotlight option to focus on one dashboard | The chosen dashboard is highlighted and comes into focus whereas all other dashboards are out of focus | This is through the elipses when selecting a visual | [6 empty] | 1 |  | Go Live Critical
1I |  | testing tool tips | [9 empty] | 1
1J |  | Analytics - Running Reports | Navigate into the sytem using a URL in a table | The relevant page of the system for the data you were viewing is opening in a new tab | [7 empty] | 1
End Test
| Total Steps: |  | 9 |  |  |  | 0 | 0
| Percentage Complete: |  | 0% |  |  |  | 0% | 0%
| Checked By: |  |  | Checked Date:
| Quality Assured By: |  |  | Sign off Date:
Testing support (screenshots/further detail)
1A - screenshots
1B - screenshots
1C - screenshots

## Problems & Queries Tracker
ID | Created By | Created | Title | Description | Raid Type | Criticality | Actions | Action Comments | Assigned to | Action Completion Date | Sign-off status | Modified By | Assigned Area | Days on Tracker
[5 empty] | Decision/Issue/Type/Risk | Low/Medium/High | Completed/Raised/In Progress |  |  |  | Approved/Not Approved |  | OneAdvanced/Customer
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15