## Suggested 6 Months Plan
Suggested six month comms plan
Communication | Timing | Key take home message | Key Stakeholder(s) | Any # or campaign names | Call to action | Channel | Responsibility | Date | Resources | Resources + | Complete
This is a suggested six month communications plan to get you started. A good cadence for communications via different channels would be twice a month, once you've launched! Think about how you can weave in stories from across your organisation to support your comms. | These are just suggested timings for comms - please re-work them to meet your project plan | Boil your communication down to a single take home message you can refer back to - this will help ensure your communication is succinct and clear. | Think about who this communication is for, you'll want to tailor your messaging depending on different stakeholders. | Are you using any hashtags or campaign names to create a sense of excitement around using the new system? Keep track of them here! | All good comms have a call to action (CTA) - this needs to be a link to part of the system asking people to do something! There should always be a CTA. | Which medium of communication are you going to us to send this? Slack, Teams, Workplace, Email or something else? Think about using a multitude of channels so there are multiple opportunities for people to see the communication. | Who is responsible for making sure this communication goes out? | When is it going out? |  |  | Has the communication gone out?
Roll-out of the system | Month 1-2
Example: Email to highlight the business benefits related to successfully adopting Continuous Performance Management. Share more around what's expected from them (leading by example etc.) and how success will be measured | 8 weeks pre-launch | We need you to support the roll-out of the system and advocate about it to everyone within the business | Senior Leadership | Example: Let's thrive together #thrivetogether | Champion the system | Presentation |  |  | Continuous Performance Management Training Deck
Example: Short and snappy email from the CEO letting everyone know as of XXX [date] Clear Review will be implemented, detailing why and including a short video that explains the system | 6 weeks pre-launch | "We want to support and invest in our people" | Everyone |  | Let's do this together | Live or recorded video / Email |  |  | Template 1
Example: Email or blog post around your performance management approach and timelines. Summary of expectations and benefits (approach more motivational to staff and saves time and effort managing team etc) | 4 weeks pre-launch | This is great for your personal development and will help improve company culture | Managers and Employees |  | Let's change things for the better | Email |  |  | Introducting Performance Development (video)
Example: Email to outline training plans and approach | 3 weeks pre-launch | We're going to give everyone training around why we're making these changes | Everyone |  | Sign up for the training |  |  |  | Continuous Performance Management Training Deck
Example: Email to outline training plans and approach | 2 weeks pre-launch | We want to ensure everyone knows how to use the system | Managers and Employees |  | Have you had your system training
Example: Email to gain buy in and reiterate what's in it for them / why should they bother | 1 week pre-launch | Managers feel like the "own" the system and processes | Managers |  | Are you onboard | Email |  |  | Benefits of Performance Development & Template 2
Launch | Month 2
Example: Email announcing the launch of the new system, reminder of what it does (track goals, feedback and check-ins) and how to access | At launch | People can now login and start using the system | Everyone |  | Join now | Email or Blog |  |  | Template 3
Launch celebration Involve senior leaders and have a live kick-off either in person or virtual or a video recording or blog for leaders to share hopes and expectations | At launch | We want everyone to login to the system and do X [example: book a check-in, leave some feedback and set a personal development objective] | Everyone |  | Login to the system | Live or recorded event, video or blog post
Incorporate training into onboarding / induction materials | At launch | Set expectations with new employees |  |  | Login and join your colleagues | Induction / onboarding materials
Keeping the momentum going | Month 3-6
Update on progress against deliverables / Examples of successes / Any feedback or lessons learned during each quarter | Quarterly | Leadership update / quarterly review | Senior Leadership |  | Review of metrics / impact / successes
The importance of having regular check-ins with team members and tips for productive check-ins | Month 3 | How managers should conduct a good quality check-in | Managers |  | How to have a good quality check-in |  |  |  | Benefits of Check-ins (video) | Check-ins Overview
The importance of giving team members feedback regularly and tips for doing it well (TIP: consider having a regular time dedicated to giving feedback i.e. Feedback Friday) | Month 3 | Giving regular feedback is important | Managers |  | When was the last time you gave feedback? |  |  |  | Feedback video | Feedback tip sheet
The importance of requesting and giving feedback regularly and tips for doing it well | Month 4 | Giving regular feedback is important | Employees |  | Give regular, quality feedback |  |  |  | Feedback video | Feedback tip sheet
How to support team members to set and achieve good quality performance and personal development related objectives (5As). | Month 4 | We want everyone in the organisation to have objectives set by [date] | Managers |  | Start setting your objectives |  |  |  | 5A's tip sheet for HR | Template 4
How to set good quality performance and personal development objectives (using 5As) | Month 4 | We want people to feel confident in setting high quality objectives | Employees |  | How to set good objectives |  |  |  | 5A's tip sheet for HR | Template 5
How to support team members to overcome obstacles and successfully achieve their objectives | Month 5 | Support your team in overcoming obstacles related to achieving objectives | Managers |  | Support your team to set good objectives |  |  |  |  | Template 4
Tips for successfully achieving objectives and overcoming obstacles | Month 5 | Setting good quality objectives is easy | Employees |  | How to set good objectives |  |  |  |  | Template 5
How to have a coaching conversation / Reminders to those who have not completed their performance management tasks | Month 5 | How managers can improves on their check-ins / conversations | Managers |  | How to have a meaningful coaching conversation |  |  |  |  | Template 7
How to support managers with wellbeing conversations | Month 6 | Managers should factor in wellbeing within their conversations with their team | Managers |  | Wellbeing conversations are vital - here's why! |  |  |  | Why you should care about wellbeing one pager (for managers) | Wellbeing prompts for discussion
Run your own "wellness wednesday" session with your team to discuss the five core elements of wellbeing: emotional, social, physical, financial and digital | Month 6 | Managers who are wellbeing advocates should run this session to encourage more open dialogue about wellbeing | Managers |  | Have "wellness wednesday" session with your team |  |  |  | Survey for HR | "Wellbeing Wednesday" session tool and instructions for managers
Update on progress against deliverables / Examples of successes / Any feedback or lessons learned during each quarter | Quarterly | Leadership update / quarterly review | Senior Leadership |  | Review of metrics / impact / successes
© 2020 Clear Review - One Touch Apps Ltd ¦ www.ClearReview.com ¦ Not to be reproduced without permission