## Setup Tracker
LinearB Enterprise Setup Tracker
Phase | LinearB Article | Task | Description | Required | Owner | Status | Verification | Notes | Completed By
Phase 1 | Phase 1 — Connect Systems | Connect Git Provider | Connect GitHub, GitLab, or Bitbucket organization to LinearB | Required |  | Not Started | Repositories visible in Integrations
|  | Connect Project Management Tool | Connect Jira, Azure Boards, or Shortcut | Required |  | In Progress | Tickets syncing successfully
Phase 2 | Phase 2 — Configure Metrics | Configure Release Detection | Define release branch or tag regex patterns | Required |  | Blocked | Deployments appear in metrics
|  | Configure Exclusions | Add bots or excluded users | Required |  | Done | Bot commits excluded from metrics
|  | Configure Metric Settings | Review cycle time, deployment detection, and filters | Required |  | Not Started | Metrics align with expected workflow
Phase 3 | Phase 3 — Teams | Create Teams | Create engineering teams and groups | Required |  | Not Started | Teams visible in dashboards
|  | Map Repositories | Assign repositories to teams | Required |  | Not Started | Repo mapping verified
|  | Map Boards / Projects | Map PM boards or projects to teams | Required |  | Not Started | Tickets appear in team views
Phase 4 | Phase 4 — Automation | Enable LinearB AI Services | Enable AI services for organization | Recommended |  | Not Started | AI insights visible
|  | Enable WorkerB | Configure Slack or Microsoft Teams notifications | Optional |  | Not Started | Notifications working
|  | Configure gitStream | Enable automation workflows | Optional |  | Not Started | PR automation triggers
Phase 5 | Phase 5 — Verification | Verify Dashboards | Validate metrics dashboards populate correctly | Required |  | Not Started | Dashboards show real data