## 2X Client Setup
2X Solutions Onboarding Guide
Responsible Party | Task | Description | Comments | Completed
Provide Staff Contact Information for Setup
| Provide Staff Contact Information for Setup | Submit the “Request for Staff" worksheet to 2X Solutions containing all staff emails and phone numbers required for setup.
Telecom Account Setup
| Telecom Company Back Office Access | Select a staff member to gain view-only access to the telecom company's back office. No action or setup required.
| Coordinate Meeting with Telecom IT Specialist | Set up a meeting with your telecom specialist to collaborate on setting up and structuring your workflow queue lines.
| Outbound Callout Number | Decide if you prefer local or toll-free numbers to be displayed as your outbound caller ID.
| Set Up Queue Line Callback Number | Provide a queue line number where a 2X connected call will transfer to your representatives. Also, if a customer calls back the 2X outbound number, we will forward the call automatically to your provided queue number. The queue numbers are specific to each workflow. Your queue line number is set at the 2X back office workflow level.
| Confirm No Pre-Recorded Messages on Queue Line | Ensure there are no pre-recorded messages placed on the queue lines. This prevents delays when transferring calls from the 2X system.
| Select Call Recording Option | On the 2X setup page, choose whether to enable audio recordings alongside the standard call transcripts that are provided. If you set up audio recordings, confirm that you have included a notification to record calls in your scripts. Note: there is a small additional cost per recording.
| Register Outbound Numbers | 2X Solutions will register your outbound number with the 'Free Call Registry,' Once registered, you will receive an email from the registry. It’s essential to complete the final step immediately. (Next step: Highly Recommended) You will need to Re-register with the Free Call Registry every 180 days to safeguard your number from spam. Long-term, consider a permenant registration and branding company to ensure your calls are not marked as spam. Contact 2X for options.
Workflow and Script Creation / Prompt & Fine-Tuning Training
| Schedule Workflow & Script Training with 2X | Set up a meeting with 2X to collaborate on creating your call workflow. This includes developing scripts, addressing common customers questions, and incorporating regulatory or company compliance guidelines to ensure effective AI training and deployment.
| Input Company Business Hours in 2X Back Office | Enter your company’s business hours into the 2X back office to ensure calls are scheduled and managed within your operational timeframe. Make sure you have created a way to capture after-hour call backs.
| Set Company Time Zone in 2X Back Office | Set your company’s time zone in the 2X back office to ensure accurate alignment of workflow calls with your business hours.
| Submit "Company and Customer Persona" Worksheet | To help us train the AI to represent your business and engage your customers effectively, we need you to create two simple personas: a company persona and a customer persona. Complete the "Company and Customer Persona Worksheet" in the 2X Setup section in your back office.
| Assign a Workflow Name | Choose a clear and descriptive name for your workflow (e.g., "Aged Leads") to help identify its purpose. This allows us to assign a specific workflow ID and ensures all team members understand which workflow they are working from. A "Sample Workflow Worksheet" is available in the 2X back office for the next few steps.
| Describe the Workflow | Provide a definition of this workflow to help train the AI. Example of “aged leads”: This workflow focuses on reengaging individuals who have previously inquired about our services. The goal is to reignite their interest and get them excited about speaking with a representative again. The key here is to keep the tone positive and helpful, ensuring the customer feels valued and encouraged to take the next step and speak to a representative. A "Sample Workflow Worksheet" is available in the 2X back office.
| Create the Workflow | Design a customized workflow for your campaign, which can include multiple calls per day and extend over several days or even months to maximize engagement and follow-up. A "Sample Workflow Worksheet" is available in the 2X back office.
| Create Scripts for the Workflow | Input all scripts for connected calls and voicemail messages directly into the workflow sheet you’ve created. 2X Solutions is available to assist in designing and refining your scripts to ensure they align with your goals and drive optimal engagement. A "Sample Workflow Worksheet" is available in the 2X back office.
| Submit "Objections and Common Qestions" Worksheet for AI Training | Provide a list of frequent questions/answers and common objections/answers specific to a workflow. Complete the "Objections and Common Questions Worksheet" in the 2X Setup section in your back office. This helps to train the AI to better respond to common customer questions.
| Submit "Reglatory and Company Compliance" Worksheet for AI Training | Identify any language that must be included or avoided to align with any regulatory requirements and business compliance policies. Complete the "Reglatory and Company Compliance Worksheet" in the 2X Setup section in your back office. This helps to train the AI to respond appropriately to sensitive subjects.
| Define any Placeholder Information | Company placeholders are used to personalize scripts by dynamically inserting specific data. For example, add a column like placeholder_lead_source to include where the customer heard about you. In the script: "Hi, Mr. Smith, you called in from ##lead_source##," would result in: "Hi, Mr. Smith, you called in from ABC News." Additional placeholder information can be found at the bottom of the sample workflow document. Important: First name, last name, phone number, and zip code do not require placeholders. These fields are automatically recognized when formatted as instructed for CSV uploads or the API integration.
| Share "Placeholder" Information with CRM Integration Team | Provide any placeholder details to the CRM integration team to ensure accurate data mapping and personalized script functionality within the workflow.
| Select Call Transfer Method (Traditional or Whisper) | Decide whether to use traditional call transfers, where the customer is connected directly, or whisper transfers, where the AI connects the call staff instantly and they can hear the conversation while on mute and press “8” to begin speaking to the customer.
CRM Integration
| Coordinate Meeting with CRM IT Specialist and 2X Solutions | Arrange a meeting between your CRM IT specialist and 2X Solutions to ensure seamless integration and alignment of workflows, data mapping, and system functionality.
| Access to API and Webhook Documentation | 2X Solutions will assure the IT specialist has full back-office access to review API and webhook documentation for integration and system configuration
| Provide your Webhook URL | Input your webhook URL along with your authorization header and token (or your preferred authentication measures) into the 2X back office setup page.
| Customer Data and CRM Placeholder Fields | Identify all essential customer record information, including metadata and placeholder fields, needed to be passed from the CRM to 2X. At a minimum, this includes the customer’s first name and phone number. Additionally, ensure any placeholder fields referenced in any workflow scripts are included.
| Request Workflow Key from 2X Solutions | IT should contact 2X Solutions to obtain the Workflow Agent ID. This ID is essential for integrating and managing workflows from your CRM system.
| Integrate Webhooks with CRM / Test | Integrate the webhook integration with your CRM to enable real-time data exchange. Define and finalize the post-webhook result processes to ensure accurate data handling. Test Webhooks as outlined in 2X backoffice.
| Integrate API Code with CRM / Test | Implement the API code to connect your CRM with 2X Solutions. This integration enables seamless data sharing and workflow automation between the systems. Verify acurate API data transfer.
| CSV File Formatting and Upload Guide for Non-API Users | For Non-API users, follow the instructions for formatting and uploading CSV files in your 2X back office
Back Office and Inbound Call Team Training
| Schedule 2X Back Office Training | Identify and gather the appropriate team members for a comprehensive walkthrough of the 2X back office and tips on training the staff to answer the AI calls. Typically, this includes an operations leader and a sales manager.
| Train Operations Staff on 2X Back Office Tools and Insights | Provide back office staff the training to utilizing key 2X back office features, including call data, scripts, transcripts, and important system settings like pausing the system. This training ensures team members can efficiently navigate the platform and leverage its tools for improved performance and decision-making.
| Provide Call Staff with Workflow Scripts and Call Handling Instructions | Supply the scripts to train the staff that will be taking calls. The scripts and additional training tips will help them identify the workflow and purpose of the call along with effective response techniques. If using whisper transfer, we will provide instructions on how to utilize this feature for seamless call connection.